## Slide 1: ENG0001E: Engineering Management - Level 2
Module 09: Engineering Contractor ‘s Document Preparation & Issue

## Slide 2: Engineering Contractor’s Document Preparation & Issue
  Engineering and design documents will be developed by the Licensors and DECs (DEC). Design document deliverables developed by the Licensors and DECs will include the following:
      Drawings
      Specifications
      Calculations
      Reports and Studies
  The PMT will review and monitor the development of Engineering and Design documents produced by the Licensors and DECs via the participation in Reviews and Audits together with formal reviews of documents and drawings submitted to the PMT throughout the life of the project.

## Slide 3: Drawings
Specific drawing requirements for the project are described in the PDS/CAD Procedures Manual. Key issues regarding drawing production by Licensors and DEC include:
Design drawings will utilize computer aided design and drafting as described in Project Information Management section.
Drawings for reports / studies will be A4 or A3 sized sheets, while P&IDs, flow diagrams, construction drawings, etc. will generally be A1 sized.
The J3 Program specific title block will be issued to all DECs for use.
J3 Program specific drawing numbering system will be used by all DECs and is defined in the PCPM.
Original, signed drawings will be retained by the Licensor and DECs Project Document and Data Management (PDDM) group for issue and file retention in line with their internal procedures.
Drawings will be Reviewed and Approved in line with the requirements set out in the TRAM and is detailed in the PCPM.
Project deliverables developed by the Licensors and DECs will be Reviewed and Approved in line with the requirements set out in the Technical Review and Approval Matrix (TRAM) issued for the J3 Program.

## Slide 4: Drawings
The two main types of engineering drawings include:
  Design basis
  Production drawings
Key Steps:
DEC Discipline Lead
Obtain required
approvals
DEC Disc Lead / Doc Ctrl
Issue drawings and
maintain originals in
project files
7
6
PMT CAD Coord
Establish a
standard drawing
format
DEC Discipline Lead
Assign unique
number to each
drawing per standard
DEC Engineer / Design
Prepare drawings and
Name electronic files
In consistent manner
DEC Engineer / Design
Ensure drawings
contain a unique
revision number
1
3
4
2
DEC Engineer / Design
Perform required
checks and
reviews
5
DEC Engineer / Design
Revise drawings
if required
8

## Slide 5: Drawing Numbering
The numbering scheme has been picked up from Project Coordination Procedure for J3-PCP-08-005-00 Drawing and Document Numbering System.
  Example:
  Group 1: Document Category Code normally has three characters. The three-character identifier is made up of the discipline code letter and two digits that define the drawing type.
  Group 2: Project/Complex/Unit identifier and it is a six digit alphanumeric code. (Refer to the Project WBS). E.g. AYZ261 (Paraxylene Unit in Aromatics Complex)
  Group 3: Section Number, (This is an Optional field), Contractor to include an additional section number where the Work Breakdown Structure (WBS) does not provide sufficient granularity to fit their work processes.
  Group 4: Drawing sequence number and it is numbered sequentially from 001.

## Slide 6: Drawings – Key Points
Detailed practices to control development
Numbering convention communicated to project team:
  Engineering Contractor’s standard format or,
  J3 -specific format
DEC Discipline Leads assign and coordinate numbering
Procedures define requirements for review and approval

## Slide 7: Technical Review and Approval Matrix - TRAM

## Slide 8: DOR-Division of Responsibility Matrix
Sr No | Deliverable / Activity Description | X - Full Responsibility / Final Doc Release |  |  | Note : The activity shown under TPI/TCM/TICB is to be read in conjunction with commercial terms for execution for chargeable/lum-sum basis. | 
 |  | X1 - Prelim Resp / Base doc / Input / Participate |  |  |  | 
 |  | A - Review & Approve |  |  |  | 
 |  | R - Review & Comment |  |  |  | 
 |  | LICENSOR | EP CONTRACTOR |  | PMC | RIL
 |  |  | Basic engg. scope | Detail engg scope |  | 
 |  |  | TPI | TPI |  | 
1.5 | PIPING AND INSTRUMENTATION DIAGRAM (P&ID) |  |  |  |  | 
1.5.1 | PIDs shall contain following information |  |  |  |  | 
 | All equipment including spare equipment |  |  |  |  | 
 | All process piping lines with sizes |  |  |  |  | 
 | Utility lead lines & Line specifications |  |  |  |  | 
 | Service codes or symbols |  |  |  |  | 
 | Valves, Relief System requirements |  |  |  |  | 
 | Major relief valves with set pressure |  |  |  |  | 
 | Piping interconnections for drains |  |  |  |  | 
1.5.2 | Issue PIDs for Approval |  |  |  |  | 
 | PDP Section | X | R | R |  | A
 | Non PDP Section |  | R | R |  | A
1.6 | PIPING LINE LIST (LINE DESIGNATED TABLES) |  |  |  |  | 
 | PDP Section, Non PDP Section | X1 | R |  |  | R
1.6.2 | Periodically Issue LDT in agreeed format as editable copy |  |  |  |  | R

## Slide 9: Specifications
Specification for use on the J3 program will be developed and issued to all Licensors and DECs. These shall be maintained throughout the life of the project and update issued as required.
Where specifications are required by Licensors and/or DECs that do not exist within the standard specifications issued for the Program these shall be developed by the DEC and issued to the PMT/Reliance for Reviewed and Approved in line with the requirements set out in the TRAM.
In case of conflict between this document and other project specific standards / specifications, the matter shall be referred to PMT / Reliance.
The order of precedence of documents to be used on this project is a follows:
  Indian Government Statutory Rules and Regulations
  Requisition Data Sheets
  Requisition and Specifications
  Any mandatory requirements set out by RIL in Project Procedures
  International Codes and Standards

## Slide 10: Specifications
Specifications will be produced using appropriate industry codes and standards, local (e.g. OISD etc) and J3 standards and will use J3 format. The specifications will be customized in order to provide equipment and materials with the required level of quality for the function the equipment is performing.
Specifications will be turned over to DCC for issue to Licensors and DECs and file retention.

## Slide 11: Specification Numbering
Group 1 | The specification type will be one of the following designators.
 | GU - Guideline.
 | SS - Standard Specifications.
 | PS - Project Specifications.
Group 2 | Commodity Identification code comprises of a Commodity Group code and Sequence Prefix if applicable and may be up to six characters (EC denotes Electrical)
Group 3. | Section Number, (This is an Optional field), Contractor to include an additional section number where the Work Breakdown Structure (WBS) does not provide sufficient granularity to fit their work processes.
Group 4 | This is the specification sequence number which begins at 001 for each commodity type.

## Slide 12: Specifications
  Describe equipment, materials, and construction methods for the project
  Typically included in purchase orders / subcontracts
  Key Steps:
DEC Discipline Lead
Obtain required
approvals
and record
DEC Disc Lead / Doc Ctrl
Issue specs and
maintain originals in
project files
7
6
PMT Leads
Establish
specification
source and format
DEC Discipline Lead
Assign unique
number to each spec
per standard
DEC Engineers
Prepare Spec and
Name electronic files
In consistent manner
DEC Engineers
Ensure specs
contain a unique
revision number
1
3
4
2
DEC Engineers
Perform required
checks and
reviews
5
DEC Engineers
Revise
specifications
if required
8

## Slide 13: Specifications – Key Points
  Project specific requirements
  Specifications prepared by each discipline
  Internal review and approval
  Formal issue / distribution
  PMT review and acceptance
  Numbering system consistent with drawings

## Slide 14: Calculations
Calculations will be prepared by Licensors and DECs as necessary to support the design. Analytical software programs, which are not already qualified by PMT/Reliance and have been used for calculations, will be subject to approval by PMT/Reliance.
Completed formal calculations developed by the DEC that support the final will be issued to the PMT/Reliance and will be Reviewed and Approved in line with the requirements set out in the TRAM.
Calculations will be turned over to PMT/Reliance for issue and file retention in line with requirements defined in the contract.

## Slide 15: Calculation Numbering
Group 1A | Commodity Identification code comprises of a Commodity Group code and Sequence Prefix if applicable and may be up to six characters (MPP denotes pump)
Group 1B | Data Sheet Identifier. Always ‘D’ except for Process Data Sheet which shall be ‘’BD’
Group 2 | Project/Complex/Unit identifier and it is a six digit alphanumeric code. (Refer to the Project WBS).
Group 3. | Section Number, (This is an Optional field with the exception of Instrumentation), Contractor to include an additional section number where the Work Breakdown Structure (WBS) does not provide sufficient granularity to fit their work processes. Instrument Datasheets shall always have a six character number, if section number is not used zeros shall be inserted, no space or dash shall be inserted between the section and sequence number, (i.e, 170113 or 000113).
Group 4 | Data sheet sequence number commencing at 001.

## Slide 16: Calculations
Calculations compiled to:
  Form the basis of design
  Maintain a record of the basis of design
Key Steps:
DEC Engineers
Obtain required
approvals
and record
DEC Disc Lead / Doc Ctrl
Issue calculation if
needed and maintain
originals in project files
7
6
PMT Engineers
Document basis
and objective of
calculation
DEC Discipline Lead
Assign unique
number to each
calculation
DEC Engineers
Prepare Calculation
And Name electronic
Files in consistent
manner
DEC Engineers
Ensure calculations
contain a unique
revision number
1
3
4
2
DEC Engineers
Perform required
checks and
reviews
5
DEC Engineers
Revise calculation
if required
8
DEC Engineers
Ensure software is
validated and
verified
3

## Slide 17: Calculations – Key Points
Considerations:
  Supplier data availability
  Compliance with Engineering Contractor’s standard engineering practices
  Limited in scope
  Results from revised calculations must be shared
Validation of software / calculation processes
Calculations not normally issued to PMT

## Slide 18: Engineering Study Reports
Licensors and DECs will perform studies and prepare reports as defined in the Scope of Work. These shall be issued to the PMT/Reliance Reviewed and Approved in line with the requirements set out in the TRAM.
  Engineering studies will be prepared in a standard format established for the project.
  Studies will be turned over to PMT/Reliance for issue and file retention.

## Slide 19: Reports and Studies
Required for special needs such as:
  Process / Utility studies
  Environmental permit report
Key Steps:
DEC Discipline Lead
Obtain required
approvals
and record
DEC Disc Lead / Doc Ctrl
Issue reports /studies
and maintain originals
in project files
7
6
PMT Leads
Establish report /
study format
DEC Discipline Lead
Assign unique
number to each
report / study
DEC Engineers
Prepare Report and
Name electronic files
In consistent manner
DEC Engineers
Ensure reports /
studies contain a
unique revision number
1
3
4
2
DEC Engineers
Perform required
checks and
reviews
5
DEC Engineers
Revise reports /
studies
if required
8

## Slide 20: Study / Report Numbering
Group 1 | Document Category Code. and Report Identifier suffix ‘R’. Various documents produced by DEC shall indicate a code for type / category of drawings. This is required to suit the documentation system in Reliance so that the documents are stored category wise to enable easy and quick retrieval. For example G21 denotes Block Diagram.
Group 2 | Project/Complex/Unit identifier and it is a six digit alphanumeric code. (Refer to Project WBS).
Group 3. | Section Number, (This is an Optional field), Contractor to include an additional section number where the Work Breakdown Structure (WBS) does not provide sufficient granularity to fit their work processes.
Group 4 | Study Report Sequence Number commencing at 001.

## Slide 21: Reports and Studies – Key Points
Engineering Contractor’s internal or RPMG deliverables
General reference software
Checks and reviews
Numbering system consistent with drawings
Supporting cost estimates

## Slide 22: Other Deliverables
Other deliverables not falling into the categories listed above but required to support the development and construction of the J3 program and prepared by the Licensors and DECs shall be issued to the PMT/Reliance for review and approval in line with the requirements set out in the TRAM.

## Slide 23: Wrap up
Mandatory bullet input from each group at the conclusion of each module
Highlights:
Pluses:
Deltas:
Proposed path forward for future:
Instructor shall compile a composite